Project Management Plan

<Pomodoro>

West Ukrainian National University

Computer Science

Ternopil, Ukraine

Revision History

| Version Number | Date of Issue | Author(s) | Brief Description of Change |
| --- | --- | --- | --- |
| 0.1 | 26.02.2026 | Volodymyr Homut | Initial Draft of the Project Plan. |
| 0.5 | 20.03.2026 | Denys Fedyna | Reviewed WBS and updated Staffing Plan. |
| 1.0 | 22.03.2026 | Volodymyr Homut | Final approved version for development. |

Table of Contents

Introduction	2

Project Scope	2

Milestone List	2

Communications Management Plan	2

Cost Management Plan	3

Risk Management Plan	3

Staffing Management Plan	3

# Introduction

The "Pomodoro" project aims to develop a simple and intuitive web application to help users manage their time effectively. The Pomodoro technique is a widely used time management method that enhances focus and productivity by incorporating structured work and break intervals. This Project Management Plan outlines the approach, scope, schedule, and management processes for developing the application within the academic semester timeline.

# Project Scope

The scope of the Pomodoro project includes the design, development, and testing of a web-based Pomodoro timer application.

Included in the scope are:

- Start / Pause / Reset functionality.

- Custom session duration settings (short and long break logic).

- Session counter and basic productivity statistics.

- Integrated background focus music/ambient sounds.

- Responsive UI design built with React and Vite.js, utilizing browser Local Storage for session tracking.

Excluded from the scope are: Chrome browser extensions, mobile native applications, cloud synchronization, multi-user accounts, and integration with external API services.

# Milestone List

The below chart lists the major milestones for the Pomodoro Project:

| Milestone | Description | Date |
| --- | --- | --- |
| Project Initiation & Charter | Approval of the project vision, charter, and management plan. | 25.02.2026 |
| Requirements & UI Design | Completion of the user interface design and finalization of technical requirements. | 27.03.2026 |
| Core Logic Coding | Completion of the timer logic, break logic, and local storage integration using React. | 08.04.2026 |
| Testing & Debugging | Completion of UI/UX testing, bug fixing, and responsiveness checks across browsers. | 20.04.2026 |
| Final Release & Presentation | Deployment of the application to Vercel and final project presentation. | 28.04.2026 |

# Communications Management Plan

Effective communication is critical for the success of this academic project. The team will utilize the following communication and tracking methods:

| Communication Type | Description | Frequency | Format/Tool | Owner |
| --- | --- | --- | --- | --- |
| Sprint Planning & Status | Reviewing tasks, progress, and blockers for the active sprint. | Weekly | Telegram / Discord | Project Manager |
| Task & Issue Tracking | Tracking individual task status (To Do, In Progress, Done) via Kanban board. | Daily (As needed) | Jira | Entire Team |
| Code Collaboration | Code reviews, pull requests, and version control. | Continuous | GitHub | Team Lead |

# Cost Management Plan

Because the Pomodoro application is an internal educational project, the total budget is $0. All tools used are free or open-source. No external procurement, purchasing, or cost baseline management is required for this project

# Risk Management Plan

The approach for managing risks on the Pomodoro project includes identifying potential issues early and implementing simple mitigation strategies.

- Risk: Schedule delays due to high academic workload and limited development time.

  - Mitigation: The Project Manager will enforce strict task tracking via Jira Sprints. Tasks are prioritized so that the core environment (Vite, React, routing) is set up first, followed by the core timer logic, ensuring a working product is always ready for submission.

- Risk: Loss of user session data. Because the app uses browser Local Storage instead of a cloud database, clearing browser cache will delete statistics.

  - Mitigation: The development team will include a clear UI notification informing users how their data is stored, minimizing user frustration.

# Staffing Management Plan

The Pomodoro project will be developed by a core team of 5 members. The roles and responsibilities are defined as follows:

- Denys Fedyna (Project Director / Team Lead): Responsible for overall technical leadership, architecture decisions (React/Vite setup), and coordinating the development team.

- Volodymyr Homut (Project Manager): Responsible for tracking project progress, managing sprints and the product backlog in Jira, handling documentation, and ensuring academic deadlines are met.

- Eduard Tuhanov (Software Engineer): Responsible for front-end development, UI design implementation, and responsive layout coding.

- Roman Kravets (Software Engineer): Responsible for implementing the core Pomodoro timer logic, start/pause/reset functions, and break intervals.

- Artem Boychuk (Software Engineer): Responsible for implementing data persistence using Local Storage, statistics tracking, and background audio integration.